## Overview
Guideline for selection review participants
Classify | Key Work products | Template / Form ID | Activity Group | Process ID | Review Type | Review Procedures |  |  | Review Documentation |  | Checklist needed? | Checklist ID | Review Cycle | Project Responsibilities(Roles)
[5 empty] | Peer Review | Written review | Review Meeting | Workshop | Checklist | Reviw Master |  |  |  | Overall PjM | Release Manager | QDL | QD SW | CM | Group Leader Functional Safety | Functional Safety Manager | Group Leader SYS Engineering | Lead SYS Engineer | Sys Analyst | Sys Architect | Group Leader D&D SYS Testing | SYS Test Manager | SYS Tester | SYS Integr Test Manager | SYS Int Tester | Overal Test Manager (TtM) | SW Project leader | SW Analyst | SW Architect | SW Module Designer | SW Integrator | SW developper | SW Module tester | SW Int Tester | SW Test Manager | SW tester
SW Development | Software Requirements Specification |  | I2P-20-10-20-10-10 | SWE.1 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8347 | SW Release |  |  |  | I |  |  | I |  |  | S | S | [6 empty] | A | R/S | S |  |  | S |  |  |  | S
| Software Architecture Design | Rhapsody->DOORS | I2P-20-10-20-10-20 | SWE.2 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8348 8845 | SW Release |  |  |  | I |  |  | I | [10 empty] | A | S | R
| Software Module and Unit Design (design reivew) | Matlab->Rhapsody->DOORS | I2P-20-10-20-10-30 | SWE.2 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8350 8330 8846 | SW Release | I |  |  | I |  |  | I | [10 empty] | A | S | S | S |  | R
| Software Module and Unit Design(Code and Model) | Matlab->Rhapsody->DOORS | I2P-20-10-20-20-40 | SWE.3 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8352 8388 8395 | SW Release |  |  |  | I |  |  | I | [10 empty] | S |  |  | S |  | R | S
| ASW Release Note | Internal defined Template |  |  | ✔ |  | ✔ |  |  | ✔ | no | / | SW Release | [5 empty] | I | I |  | I | I | [7 empty] | A | S | S |  | R | S
| Risk Classification (module classification) | 8325 | I2P-20-10-20-40-20 | SWE.3 | ✔ |  | ✔ |  |  |  | no | / | SW Release |  |  |  | I |  |  | I | [9 empty] | A | S | S | [6 empty] | R
Test Engineering | Master Test Plan | 8316 | I2P-20-10-60-10-10 | ENG.10 | [6 empty] | yes | 8500 |  |  |  | S | I |  |  | I |  | A/S |  |  | A |  |  | S |  | R | [8 empty] | S
| SW Module Test Plan | 8517 | I2P-20-10-20-10-40 | SWE.4 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8340 | Once |  |  |  | I |  |  | I | [9 empty] | A | R |  |  |  |  | S
| SW Module Test Specification | DOORS | I2P-20-10-20-20-40 | SWE.4 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8353 | SW Release |  |  |  | I |  |  | I | [10 empty] | S |  |  |  |  | R
| SW Module Test Report | 8519 | I2P-20-10-20-20-40 | SWE.4 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8832 | SW Release | [6 empty] | I | [10 empty] | A |  |  |  |  | R
| SW Integration Plan | 8831 | I2P-20-10-20-30-10 | SWE.5 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8589 | SW Release |  |  |  | S |  |  | I | [10 empty] | A/S |  |  |  | R
| SW Integration Test Plan | 8517 | I2P-20-10-20-40-10 | SWE.5 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8589 | SW Release |  |  |  | S |  |  | I | [9 empty] | A | S |  | S | [5 empty] | R
| SW Integration Test Specification | 8518 | I2P-20-10-20-40-10 | SWE.5 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8354 | SW Release |  |  |  | S |  |  | I | [12 empty] | S |  |  |  |  | R | A
| SW Integration Test Report | 8519 | I2P-20-10-20-40-30 | SWE.5 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8832 | SW Release |  |  | C | S |  |  | I | [17 empty] | R | A/S
| SW Test Plan | 8517 | I2P-20-10-20-40-20 | SWE.6 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8392 | SW Release |  |  |  | S |  |  | I | [9 empty] | A | S | S | [6 empty] | R
| SW Test Specification | 8518/DOORS | I2P-20-10-20-40-20 | SWE.6 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8394 | SW Release |  |  |  | S |  |  | I | [11 empty] | S | [6 empty] | A | R
| SW Test Report | 8519 | I2P-20-10-20-40-40 | SWE.6 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8832 | SW Release |  |  | C | S |  |  | I | [18 empty] | A/S | R
| System Integration Plan | 8831 |  | SYS.4 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8393 | SW Release |  |  |  | S |  |  | I |  |  |  | S |  |  |  | R |  | A | S
| System Integration Test Plan | 8517 | I2P-20-10-60-10-60 | SYS.4 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8393 | SW Release |  |  |  | S |  |  | I |  |  | S |  |  |  |  | R |  | A | S
| System Integration Test Specification | 8518 | I2P-20-10-60-10-60 | SYS.4 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8588 | SW Release |  |  |  | S |  |  | I |  |  |  | S |  |  |  | A | R/S
| System Integration Test Report | 8519 | I2P-20-10-60-30-10 | SYS.4 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8832 | SW Release |  |  |  | S/C |  |  | I | [7 empty] | A | R/S
| System Test Plan (function) | 8517 | I2P-20-10-60-10-20 | SYS.5 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8355 | SW Release | S |  | S | S |  |  | I |  | S |  |  | A | R | S |  |  | A/S | S
| System Test Specification (function) | 8518/DOORS | I2P-20-10-60-10-30 | SYS.5 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8367 | SW Release | C |  | S | C |  |  | I |  |  | S |  | A | R | S |  |  | C | C
| System Test Report (function) | 8519 | I2P-20-10-60-30-20 | SYS.5 | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8832 | SW Release |  |  | S/C |  |  |  | I | [5 empty] | A/S | R
| Master Test Report | 8519 | I2P-20-10-60-10-10 |  | ✔ |  | ✔ |  | ✔ | ✔ | yes | 8832 | SW Release | C |  | S | S |  |  | I | C |  |  |  |  | S |  | S |  | R | C | [7 empty] | S
Note on AE3: Yan, Xiaojuan: Tobias Kuhn
Note on D4: Le, Thi Ngoc: Activity - Review software requirements specification
Note on D5: Le, Thi Ngoc: Activity: Verify software architecture
Note on M5: Zhang, Fiona: 1) review checklist software architecture specification_8348 2) review checklist software architecture specification with Rhapsody_8845
Note on D6: Le, Thi Ngoc: Activity - Review Software Module & Unit Design
Note on M6: Zhang, Fiona: 1) review checklist software module and unit design_8350 2) review checklist modelbased module design_8330 3) review checklist software module and unit design with Rhapsody_8846
Note on D7: Le, Thi Ngoc: Activity - Perform Code and Test Case Review
Note on M7: Zhang, Fiona: 1) review checklist code_8352 2) review checklist code("model based")_8388 3) Manual Review of MISRA Rules_8395
Note on D9: Le, Thi Ngoc: Develop software test strategy
Note on D10: Le, Thi Ngoc: Activity - Review and release master test plan
Note on D11: Le, Thi Ngoc: Activity - Review and release software module test plan
Note on D12: Le, Thi Ngoc: Activity - Perform Code and Test Case Review
Note on D13: Le, Thi Ngoc: Activity - Assess and communicate maturity of software modules
Note on D14: Le, Thi Ngoc: Activity - Review (initial) Build List and Software Integration Plan
Note on D15: Le, Thi Ngoc: Activity - Review and release software integration test plan
Note on D16: Le, Thi Ngoc: Activity - Review and release software integration test specification
Note on D17: Le, Thi Ngoc: Activity - Review software integration test results
Note on D18: Le, Thi Ngoc: Activity - Review and release software test plan
Note on D19: Le, Thi Ngoc: Activity - Review and release software test specification
Note on D20: Le, Thi Ngoc: Activity - Review software test results
Note on D22: Le, Thi Ngoc: Activity - Review and release system integration test plan
Note on D23: Le, Thi Ngoc: Activity - Review and release system integration test specification
Note on D24: Le, Thi Ngoc: Activity - Review system integration test results
Note on D25: Le, Thi Ngoc: Activity - Review and Release System Test Plan(s)
Note on D26: Le, Thi Ngoc: Activity - Review and Release System Test Specification
Note on D27: Le, Thi Ngoc: Activity - Review system test results
Note on D28: Le, Thi Ngoc: Activity - Summerise all test results

## Comments
Comments | 1) for Non-ASIL projects, safety manager review can be skipped.
|  | Invite in meeting | Feedback | MM Inform
Project Responsibilities | R: Responsible = Execution(document auther) | Must | Must | Must
| A: Accountable = Decision | Must | Must | Must
| S: Supportive = Support | Must | Must | Must
| C: Consulted | Must | optional | Must
| I: Informed = Information | Must | optional | Must
Note on E9: [线程批注] 你的Excel版本可读取此线程批注; 但如果在更新版本的Excel中打开文件，则对批注所作的任何改动都将被删除。了解详细信息: https://go.microsoft.com/fwlink/?linkid=870924 注释: "Must" colleagues must feedback to the review in Review Master. E.g. "No comment", "comment has been logged in review checklist"
Note on F9: [线程批注] 你的Excel版本可读取此线程批注; 但如果在更新版本的Excel中打开文件，则对批注所作的任何改动都将被删除。了解详细信息: https://go.microsoft.com/fwlink/?linkid=870924 注释: Send out meeting minutes or review checklist information to the "Must" colleagues.

## Document States
Initial（template） | o This is the default state and only to be used for the raw template.
In work (during preparing) | o This is the normal state during creation of the work product.
Submitted (during review) | o This means that a review has taken place and it has been successfully passed and the document is submitted to the line manager for an approval.
Accepted (review finish) | o This means that a review has taken place, all findings are taken care of and approver has accepted the work product.
Invalid (disabled) | o This is a possible state in case a work product or document becomes unusable for some reason.

## Review Procedures
Review Meeting
Task 6: Organize review
The review needs to be planned and prepared. The author selects review participants, informs about the outstanding review and sets up an appropriate review checklist (prepare according to the Overview sheet).
[Review Database] The Review Master Issue is created.
Task 7: Assemble work product
The author collects a set of specific documents based on a summary of project requirements, typically including: • Project documents concerned, • Background information in support of development and with regard to development stages, • Explanations, • Checklist with reference to the object reviewed, Optionally, the checklist may also be prepared by the moderator.
Task 8: Distribution of work product and invitation
Well in advance of the meeting, the inviting person (author) distributes the documents to the participants. A meeting plan including the roles, competence assignments, the schedule and a summary of earlier reviews. A definition of how long before the review meeting the reviews are to be handed over to the author and moderator is to be given in the invitation.
Task 9: Hand in of pre-review results
Author should check items in checklist. The participants has to read the document under review and to keep review notes and comments which are to be handed over to the author. The author have to define in the invitation the how long before the review meeting the written reviews are to be handed over.
Task 10: Review meeting (refer to "Review_Meeting_Template" sheet)
Team 'brainstorming' to discover any findings, (only then!) tick off the checklist, identify and document the mistakes; the meeting should go on for no longer than two hours. Responsibility assignment, definition of times/assessment of efforts required to eliminate the shortcomings.
Task 11: Document findings
The meeting organizer writes down and keeps a list of mistakes discussed. Decisions are documented as well. The meeting organizer distributes the minutes to the other review participants. (Meeting Minute) [Review Database] The results are documented online during the meeting. Tasks and Changes Issues are generated and linked to the review master. At the end of the meeting the state of the review master is set to “performed”.
Decision 1: Re-review necessary?
It must be decided by the team: • if the review was passed, • if moderate findings (which need a rework/modification), or • if severe OOS results (out-of-specification results, which need solid changes to the review item) were found. The decision about the authorization of the next phase: • Accepted, • Accepted with the obligation of modification, or • Not Accepted, needs to be taken and documented. Remark: If there are modifications agreed upon, an appropriate time span is given to the author to correct the mistakes. These modifications are then checked by the moderator for completeness.
Task 12: Escalate
Proceed as follows if a review finds any OOS (out-of-specification) results:
• OOS results are documented and rectified by means of suitable corrective measures at project level involving all levels of the hierarchy as appropriate, i.e., all people from the developer to the software/hardware project manager and the project manager level. To achieve this aim, the action taken to remove the OOS result is added to the central plan of project tasks.
• Review documentation also includes OOS results that cannot be rectified at project level. These are escalated to the management level (depending on the organization) and followed up until the problems have been solved or until the management gives reasons for their decision not to take any corrective action.
Documentation of OOS results is kept under controlled supervision in the MKS-SI (AD-PE1-1-10).
If OOS results where found:
• the review is not passed,
• the review checklist is not signed and
• the review needs to be repeated again
Decision 2: Modification?
If it was found out by the review team, that minor changes need to be done to the review item this can be done by an obligation of the author for a modification. The completion of the modification must be checked by the proposed person (see Decision 3: ).
Task 13: Modification
The Author modifies the item according to the documented complaints in the review-checklist. He does this by keeping the time schedule for the modification.
Decision 3: Modification done?
The SWPJM checks for the completion of the modification. In case the modification was not done after the agreed time span, the SWPJM has the ability to escalate to the management level.

## General Rules for Reviews
General Rules for Reviews
The following rules are to be observed with regard to reviews:
• All team members are accepted as peers.
• Discussions are held with respect to the subject matter, i.e., in a non-accusatory manner.
• Differences of opinion are treated as a source of information and not as interference.
• To keep everybody at the same level of information, tell others what you know.
• Do not get lost in details but handle them separately.
Create a team atmosphere of trust and openness!